## Sheet1
Team 47 Product Backlog
Priority | Features | Initial Estimates (hours) | Adjust Factor | Adjust Estimate | 1 | 2 | 3
1 | Welcome Page | 5 | 0 | 5
2 | Login Page | 7 | 0 | 7
3 | Actual Login Implementation | 10 | 0 | 10
4 | Register Page | 7 | 0 | 7
5 | Actual Register Implementation | 10 | 0 | 10
6 | Admin Account | 5 | 0 | 5
7 | Create Multiple Accounts | 5 | 0 | 5
8 | User Profile | 3 | 0 | 3
9 | Deposits | 5 | 0 | 5
10 | Withdrawals | 1 | 0 | 1
11 | Transaction History | 10 | 0 | 10
12 | Spending Catergory Report | 15 | 0 | 15
13 | Income Source Report | 15 | 0 | 15
14 | Cash Flow Reports | 15 | 0 | 15
15 | Account Listing Report | 15 | 0 | 15
16 | Transaction History Report | 15 | 0 | 15
| Total: | 143 |  | 143